## Workbook Notes
Welcome to the AI Value Realization Framework Template
Quick Notes on this Template:
Purpose of this template is to provide a simple mechanism for calculating ROI on AI project
This framework is not a guideline, Just an approach that can be customized or enhanced to individual need
Refer to my supporting LinkedIn article to know more about this framework - https://www.linkedin.com/pulse/identifying-prioritizing-artificial-intelligence-use-cases-srivatsan/ -
In case if you need any info or find any bug please log issues in GitHub link attached below. Issues link will be on top of repo - https://github.com/srivatsan88/AI-Value-Realization-Framework
ROI Formula mentioned above contains 4 Component to it. Direct Benefit, Indirect Benefit, Implementation Cost and Complexity Factor. Working details of above 4 component is captured in respective tabs below Direct Benefit - Taken from Use Case details tab Indirect Benefit Factor - Taken from Indirect Benefit Factor tab Complexity Factor - Taken from Complexity Details Tab Implementation Cost - Derived from tabs - Initial project cost, Lights on operations cost, Infrastructure cost, Product buy cost.
Final ROI Calculation is available in Return On Investment Sheet
Indirect Benefit Factor and Complexity details has set of parameters and weightages. Add/Remove parameters or adjust weightages to the need of your organization
Refer to notes on individual tabs and sheet to get more details
Click on values to understand the formula. Most of the formula's are simple and straight forward

## Use Case Details
| Example 1 (Very Complex) | Example 2 (Medium Complex)
Use Case Name | Small Business Credit Scoring | Personalized Offers
Use Case Details | Machine Learning application to score existing small business customers and prioritize based on risk profile. Prioritized small business will be used for up selling or for credit limit increase | Machine Learning application to analyze user historical behavior pattern and recommend them for targeted promotional offers
Use Case Category | Increase in Topline | Increase in Topline
Line of Business | Risk | Marketing
Business Objective | Identify low risk and high value customers who are candidates for re-adjustment of credit limit resulting in Incremental revenue | Increase customer revisits by recommending them with targeted offers on products they are more likely to purchase
Business Process Criticality | Medium | Medium
Impact where AI makes wrong decision | Can result in write-offs or utilized increased limit | Not much of a Impact
Expected Direct Business Benefit | $5 million in Incremental Revenue | $5 million in Incremental Revenue
Expected Indirect Business Benefit ( in $ if known else fill in Indirect Benefit tab) | NA | Higher 3rd party seller product enrollment and engagement | Notes on Measurement of success:
Measurement of Success | List and order high Value generated in dollar terms by customers provided with pro-active limit increase using historical data and having low risk scoring profile. Compare it with actual value generated Check if top 2% ordered customer generates at least 10% incremental revenue | 20% offer conversion rate out of targeted customers | Sometimes measurement of success can be difficult to define especially in case if you have data but never were able to track outcome properly. In this case you might want to experiment in real world (not decision) to capture and re-learn your model based on it Question might be why to take these use cases?. This might be something core of what your business does and you feel it might be beneficial to try intelligent solutions to bring in efficiency Yes, One can start with prototype but prototype by itself is expensive and requires co-ordination across federated team. These cases you can use the template selective section to budget experimentation phase
Use Case owner | John Doe | Jane Doe
Impacted line of business (Internal) | Risk, Marketing, Collections | Vendor, Procurement, Sales
Impacted Organization (External) | NA | NA

## Return on Investment
[6 empty] | Year 1 | Year 2 | Year 3 | Comment
Cost (Expense)
|  |  |  | Implementation Cost |  | 1646400
|  |  |  | Complexity Factor | 0.65 | 1070160 |  |  | Only on Implementation cost
|  |  |  | Infrastructure Cost |  | 31650 | 33768 | 33768
|  |  |  | Operations Cost |  |  | 547200 | 240000
Direct Benefit | Indirect Benefit Factor | Implementation Cost | Complexity Factor | Product Buy Cost
5000000 | 0.2 | 2481018 | 0.65
Benefit (Revenue)
|  |  |  | Expected Direct Benefit | 0.5 | 0 | 2500000 | 5000000
|  |  |  | Expected Indirect Benefit | 0.2 | 0 | 500000 | 1000000
Notes :
While we have above details, remember the cost is over 3 years |  |  |  | ROI (Yearly) |  | -2748210 | 2419032 | 5726232
Complexity Factor is only applicable during implmentation but indirect benefit factor is applicable throughout the project lifetime
This make applying above to ROI calculation not reliable |  |  |  |  | Total ROI | 5397054
On right hand side we will calculate y-o-y ROI for 3 years to see actual business benefit |  |  |  |  | Total Cost | 3602946
Assume 0 Direct benefit 1st year as project is getting implemented and 50% in 2nd year and 100% thereafter
[5 empty] | ROI (%) | 49.7956
ROI Calculation Notes :
Numbers used in ROI has been calculated in different tabs in this excel and pulled in here
Expected Direct Benefit is coming from Use Case Details sheet - Assumed as $5 million
50% of business benefit is expected in 2nd year and 100% there after
Complexity Factor is to account for uncertainity in executing AI projects and is applicable during the implementation phase only
ROI Calculated each year individually

## Total Implementation Cost
Cost Details | Expected Cost in $
Initial Project Cost | 1646400
Lights on Operations Cost | 787200
Infrastructure Cost | 47418 | 3 years cost
Product Buy Cost | 0
Total Cost | 2481018
Notes :
Above mentioned is total cost of project over the course of 3 years
This sheet is just rough estimate of total cost but to get actual ROI we will be using year on year cost
Check Return on Investment sheet for more details

## Initial Project Cost
Model Complexity (Fill details for only one of the complexity row per project. Create separate sheet for each project)
Project Role | Simple | Medium Complex | Complex | Very Complex | Allocated Percentage | Blended Cost $ (Per Role/Per Hour) | Tentative Project Duration (In months) | Cost (Per Role)
Product Owner |  | 1 |  |  | 1 | 120 | 12 | 230400
Scrum Master |  | 1 |  |  | 0.5 | 100 | 12 | 96000
Business Owner |  | 1 |  |  | 0.75 | 100 | 12 | 144000
AI Champion |  | 1 |  |  | 0.25 | 120 | 12 | 57600
Data Engineer |  | 2 |  |  | 1 | 140 | 12 | 537600
ML Engineer/Data Scientist |  | 1 |  |  | 1 | 140 | 12 | 268800
Data Analyst |  | 0 |  |  | 0 | 120 | 12 | 0
Operations Engineer |  | 1 |  |  | 0.5 | 90 | 12 | 86400
Software Engineer |  | 1 |  |  | 0.75 | 90 | 12 | 129600
BI Engineer |  | 1 |  |  | 0.5 | 100 | 12 | 96000
[7 empty] | Total Cost | 1646400
Notes :
Assign team structure based on complexity level of the project
Tune allocated percentage based on complexity. 100% of product manager time might be required for complex projects but simple might not be. So on
Change cost to your organization internal employee or consultant cost
Blended cost is average cost if a role requires multiple consultants. Check below for blended cost calculation
Fill in data against only one complexity row. Use separate sheet for every project
Blended Cost Calculator (Where multiple consultants at various roles are assigned for single activity)
| Project Role | Designation | contribution (%) | Cost $ (per hour)
| Data Engineer | Architect | 0.8 | 190 | Allocated 80% of time in project
| Data Engineer | Engineer | 1 | 120 | Allocated fully to the project
|  |  | Blended Cost $ | 136

## Lights On Operations Cost
Year 2 :
Model Complexity (Fill details for only one of the complexity row per project. Create separate sheet for each project)
Project Role | Simple | Medium Complex | Complex | Very Complex | Allocated Percentage | Blended Cost $ (Per Role/Per Hour) | Tentative Project Duration (In months) | Cost (Per Role)
Data Engineer |  | 1 |  |  | 0.25 | 140 | 12 | 67200 | Notes:
ML Engineer/Data Scientist |  | 1 |  |  | 0.5 | 140 | 12 | 134400 | Cost projections made for 3 years from the start of project
Data Analyst |  | 0 |  |  | 0 | 120 | 12 | 0 | Minimum Data Engineer commitment post deployment to ensure robustness of deployed data pipelines
Operations Engineer |  | 2 |  |  | 1 | 90 | 12 | 345600 | Data Scientist time post deployment for model monitoring, drift analysis and recalibration as needed
[7 empty] | Total Cost | 547200
Year 3 :
Model Complexity (Fill details for only one of the complexity row per project. Create separate sheet for each project)
Project Role | Simple | Medium Complex | Complex | Very Complex | Allocated Percentage | Blended Cost $ (Per Role/Per Hour) | Tentative Project Duration (In months) | Cost (Per Role)
Data Engineer |  | 1 |  |  | 0 | 140 | 12 | 0
ML Engineer/Data Scientist |  | 1 |  |  | 0.25 | 140 | 12 | 67200
Data Analyst |  | 0 |  |  | 0 | 120 | 12 | 0
Operations Engineer |  | 1 |  |  | 1 | 90 | 12 | 172800
[7 empty] | Total Cost | 240000

## Infrastructure Cost
| Items | Item Details | Purpose | Training hour required | Cost per hour | Cost | Total Cost over 3 years
| Compute Cost | GPU - Tesla V100 | Training Model | 5000 | 2.48 | 12400 | 12400
| Compute Cost | Regular Instance | Training Model | 5000 | 0.25 | 1250 | 1250
| Compute Cost | Regular Instance | Data Engineering | 10000 | 0.55 | 5500 | 16500 | Refer notes below
| Compute Cost | GPU - Tesla K80 | Model Deployment | 17520 | 0.45 | 7884 | 15768 | Refer notes below
| Storage Cost | 1 TB Storage |  |  |  | 500 | 1500 | Refer notes below
[6 empty] | Total Cost | 47418 |  | Reference Cost (Google Cloud)
[9 empty] | Model | GPUs | GPU memory | GPU price | Pre-emptible GPU price
|  | Notes : | [6 empty] | NVIDIA® Tesla® T4 | 1 GPU | 16 GB GDDR6 | $0.95 USD per GPU | $0.29 USD per GPU
|  | Above cost is calculated for google cloud environment | [7 empty] | 2 GPUs | 32 GB GDDR6
|  | If on premise add corresponding items to come up with infrastructure cost | [7 empty] | 4 GPUs | 64 GB GDDR6
|  | If shared infrastructure bake in exact cost to be incurred for the project | [6 empty] | NVIDIA® Tesla® P4 | 1 GPU | 8 GB GDDR5 | $0.60 USD per GPU | $0.216 USD per GPU
Training model is implementation cost, model deployment is cost post models are operationalized and Data Engineering cost is applicable in both the cycles | [9 empty] | 2 GPUs | 16 GB GDDR5
[10 empty] | 4 GPUs | 32 GB GDDR5
[9 empty] | NVIDIA® Tesla® V100 | 1 GPU | 16 GB HBM2 | $2.48 USD per GPU | $0.74 USD per GPU
[10 empty] | 2 GPUs | 32 GB HBM2
[10 empty] | 4 GPUs | 64 GB HBM2
[10 empty] | 8 GPUs | 128 GB HBM2
[9 empty] | NVIDIA® Tesla® P100 | 1 GPU | 16 GB HBM2 | $1.46 USD per GPU | $0.43 USD per GPU
[10 empty] | 2 GPUs | 32 GB HBM2
[10 empty] | 4 GPUs | 64 GB HBM2
[9 empty] | NVIDIA® Tesla® K80 | 1 GPU | 12 GB GDDR5 | $0.45 USD per GPU | $0.135 USD per GPU
[10 empty] | 2 GPUs | 24 GB GDDR5
[10 empty] | 4 GPUs | 48 GB GDDR5
[10 empty] | 8 GPUs | 96 GB GDDR5

## Product Buy Cost
Items | Purpose | Cost per hour | Total Cost
SAS
Actimize
|  | Total Cost | 0
Notes :
Use this sheet if you are buying off the shelf projects required for accelerating analytics journey

## Complexity Details
Complexity Type | Use Case Relevance (Enter 1 where applicable and 0 in case Not Applicable or Not Complex) | Enterprise Readiness Weightage (Enter weightages in % depending on your enterprise adoption)
Implementation Complexity | 1 | 20
Low Latency SLA | 1 | 15
Data Collection Challenge | 1 | 30
Business Integration Challenge | 0 | 15
Deployment Challenge | 0 | 10
Unhandeled use case pattern | 0 | 10
100
Complexity Factor | 0.65
Notes:
Add or Remove line items as required and adjust weight to one's enterprise need

## Indirect Benefit Factor
Benefit Receipient (Objective other than that solving for) | Use Case Relevance (Enter 1 where applicable and 0 in case Not Applicable or Not Complex) | Weightage indicating importance to receipient to enterprise (Enter weightages in % depending on your enterprise adoption)
Customer | 1 | 20
Vendor | 0 | 15
Merchant | 0 | 30
Internal LOB | 0 | 15
Goodwill | 0 | 10
Others | 0 | 10
100
Benefit Factor | 0.2
Notes :
Indirect benefit is factored in by assessing the benefit of AI model outside the set business objective
Say a fraud detection model with low false positives may enhance customer experience and can inturn increase customer spend
Another example is Amazon prime day sale might increase merchant participation which inturn might increase more merchant getting onboarded to Amazon marketplace

## Lookup
Competative Advantage
Increase in Topline
Increase in Bottomline
Streamline Operations Cost
Enhance Customer Experience
Regulatory Need
Indirect Revenue Contribution
New Business Opportunity